## Instructions
Resource Loading Schedule — September to Year End
Purpose | Week-by-week field resource requirement, Sept 2026 to year end, so we can see where crews are needed and when.
PMs — what to do | Open YOUR tab (named for you). Enter FTE per week against each row. FTE = full-time equivalents, e.g. 2.5 = two and a half people that week.
Two ways to enter | Both roll up identically — use whichever suits the job.
Option A — by Job | Your live jobs are already listed. Pick the Trade for the row, then enter FTE by week. Need more than one trade on a job? Copy the row and change the Trade.
Option B — by Client | Don't want job-level detail? Use the blank rows at the bottom: leave Job # empty, choose the Client and Trade, then enter FTE by week.
Cells you edit | Yellow cells only. Everything else is a formula — please don't overwrite.
Blue text | A number you typed in.
Green text | A figure pulled from another tab.
Summaries | 'Summary - Trade' and 'Summary - Client' are 100% formula driven and update themselves. Nothing to fill in there.
Adding rows | Insert anywhere between rows 4 and 400 on your tab — the summaries already cover that range.
Trades list | Held on the 'Lists' tab. If a trade is missing, add it there and it appears in the dropdowns and on the summary.
ASSUMPTION — please confirm | The trade list is a first pass and has NOT been agreed. Ken / PMs to confirm the categories before this goes out.
Weeks | 18 weeks, week-ending Saturday, 05-Sep-2026 through 02-Jan-2027 — carried over from the original file.
Source | Job, client and PM data from the 'Input - Project List' tab (205 active jobs).
EXAMPLE — how a filled row looks
Job # | Description | Client | Contract | Trade | 05-Sep | 12-Sep | 19-Sep
01-26-020 | Nova Corunna - Heater BA-2107 | Nova Chemicals Corporation | T&M | Boilermaker | 4 | 4 | 2.5
| (leave blank = plan by client) | Shell Canada Products |  | Pipefitter / Steamfitter | 2 | 2
Row 1 is job-level. Row 2 is client-level — Job # left blank. Both add into the same summary totals.

## Summary - Trade
RESOURCE SUMMARY — FTE by Trade and Week Ending
Formula driven. Pulls from every PM tab — nothing to fill in here.
Trade | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2027-01-02 | Total
Boilermaker | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pipefitter / Steamfitter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Welder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Millwright | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ironworker | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electrician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Instrumentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Insulator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scaffolder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labourer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crane Operator / Rigger | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA / QC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Supervision | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering / Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drafting / Modelling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Safety | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL FTE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Summary - Client
RESOURCE SUMMARY — FTE by Client and Week Ending
Formula driven. Pulls from every PM tab — nothing to fill in here.
Client | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2027-01-02 | Total
Aecon Industrial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ainsworth Technical LP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arlanxeo Canada Inc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CF Industries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cope Construction Co | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Diamond Petrochemicals Canada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dow Chemical Canada Inc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enbridge Gas Inc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Goodfellow Construction (1993) Ltd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H.C. Starck Canada Inc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hydrostor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Imperial Oil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interface Testing Services Inc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MN Mechanical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Nova Chemicals Corporation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shell Canada Products | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Suncor Energy Inc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TKO Industrial Services Corporation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TransAlta (SC) LP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
University of Guelph | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VIP Rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wolverine Engineering Ltd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL FTE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Barrett, Ken
RESOURCE LOADING — Barrett, Ken
Enter FTE in the yellow cells. Leave Job # blank on the bottom rows to plan at client level.
Job # | Description | Client | Contract | Trade | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2027-01-02 | Total
04-26-001 | AECON - CEPPS Modularization | Aecon Industrial | T&M | [19 empty] | 0
04-26-002 | AECON - TBM Pipe Basket - Darlington SMR | Aecon Industrial | T&M | [19 empty] | 0
01-26-099 | Nova - C9200 LEAK | Nova Chemicals Corporation | FP | [19 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL FTE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Brundage, Eric
RESOURCE LOADING — Brundage, Eric
Enter FTE in the yellow cells. Leave Job # blank on the bottom rows to plan at client level.
Job # | Description | Client | Contract | Trade | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2027-01-02 | Total
01-26-097 | Boiler 128 Ductwork Baffles | Nova Chemicals Corporation | T&M | [19 empty] | 0
01-26-045 | Nova Corunna - 28950 – Piping Demolition | Nova Chemicals Corporation | T&M | [19 empty] | 0
01-26-020 | Nova Corunna - Heater BA-2107 TLEs & Coils | Nova Chemicals Corporation | T&M | [19 empty] | 0
01-26-149 | Nova Corunna - Quench Header EPC | Nova Chemicals Corporation | T&M | [19 empty] | 0
01-26-152 | Nova Corunna - Wolverine - 29307 - Heater Tie-Ins | Nova Chemicals Corporation | T&M | [19 empty] | 0
01-26-182 | Nova Moore - FCM Y-527 and Piping Replacement | Nova Chemicals Corporation | T&M | [19 empty] | 0
01-24-334 | NOVA Moore - MENox Compliance | Nova Chemicals Corporation | FP | [19 empty] | 0
01-26-144 | Suncor Ethanol - #300664881 - 2026 Annual - Ethanol Plant Call in Supp | Suncor Energy Inc | T&M | [19 empty] | 0
01-26-100 | Suncor Ethanol - CIP Light Phase Piping | Suncor Energy Inc | T&M | [19 empty] | 0
01-26-009 | TransAlta - Superheater Drains | TransAlta (SC) LP | T&M | [19 empty] | 0
01-26-092 | TransAlta - TAN 420 Steam Tie-Ins | TransAlta (SC) LP | T&M | [19 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL FTE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Dubois, Joe
RESOURCE LOADING — Dubois, Joe
Enter FTE in the yellow cells. Leave Job # blank on the bottom rows to plan at client level.
Job # | Description | Client | Contract | Trade | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2027-01-02 | Total
01-26-121 | GoodFellow - Install & Fab Support at Pembina(A6012.01-8B-00224&00223) | Goodfellow Construction (1993) Ltd. | FP | [19 empty] | 0
01-26-111 | Shell - 26FCCUPS - OPEX - DFL | Shell Canada Products | T&M | [19 empty] | 0
01-26-112 | Shell - 26FCCUPS - OPEX - Overheads | Shell Canada Products | T&M | [19 empty] | 0
01-26-166 | Shell - WO#85445251 New Replacement ATI-31 MOC-95468 - OVERHEADS | Shell Canada Products | T&M | [19 empty] | 0
01-26-080 | Shell - 2026 NRM-Crude 2 exchangers- Wolverine | Shell Canada Products | T&M | [19 empty] | 0
01-26-079 | Shell - 26 NRM CUI CWP-47A FCCU-CE101R Capex- Wo | Shell Canada Products | T&M | [19 empty] | 0
01-26-138 | Shell - 26CR3SPS- Mechanical - OPEX - DFL | Shell Canada Products | T&M | [19 empty] | 0
01-26-156 | Shell - 26FCCUPS - Replace CF - 222 drain piping | Shell Canada Products | FP | [19 empty] | 0
01-26-010 | Shell - 26NRM-CC-309R-bundle repair - DFL | Shell Canada Products | T&M | [19 empty] | 0
01-26-197 | Shell - 5103-Piping-CPK | Shell Canada Products | T&M | [19 empty] | 0
01-26-188 | Shell - 5116-PROJ-LITTLE DIPPER SUPPORT | Shell Canada Products | T&M | [19 empty] | 0
01-26-170 | Shell - 5148 Flare Gas SO2 Minimization – Phase 2 | Shell Canada Products | T&M | [19 empty] | 0
01-26-169 | Shell - 5148 Flare Gas SO2 Minimization – Phase 2 (Fab) | Shell Canada Products | FP | [19 empty] | 0
01-26-021 | Shell - 5169-PROJ-MiscWork-RailCapPh2 | Shell Canada Products | T&M | [19 empty] | 0
01-26-066 | Shell - 85406372 KF-7 - Full Internal Inspection – NRM-KF7 - DFL | Shell Canada Products | T&M | [19 empty] | 0
01-26-051 | Shell - 85407798 2025 NRM - Jet line to Tank 8 Capex | Shell Canada Products | T&M | [19 empty] | 0
01-26-096 | Shell - Aeration Basin MOC Phase 1-6 | Shell Canada Products | T&M | [19 empty] | 0
01-26-118 | Shell - CAIR91467-GHT RPLC Steam Drain valve | Shell Canada Products | FP | [19 empty] | 0
01-26-098 | Shell - CAIR-93408-MOC95448-CPV153 | Shell Canada Products | FP | [19 empty] | 0
01-26-055 | Shell - CAIR-93571-CE-310R-Caustic ppg | Shell Canada Products | FP | [19 empty] | 0
01-26-120 | Shell - CR3/Regen Lube Oil piping CAIR000093748 | Shell Canada Products | FP | [19 empty] | 0
01-26-090 | Shell - Demo CC-218, CC-219, CC-220 | Shell Canada Products | T&M | [19 empty] | 0
01-26-091 | Shell - Fabricate CAIR93581-MOC97688-KFT244 Replacement | Shell Canada Products | FP | [19 empty] | 0
01-26-202 | Shell - Install 1500 ft of 4â€ Soybean Oil piping | Shell Canada Products | T&M | [19 empty] | 0
01-26-056 | Shell - maintenance support 2026 #85485360 | Shell Canada Products | T&M | [19 empty] | 0
01-26-131 | Shell - NRM - WO#85263243 - Pump Removal | Shell Canada Products | T&M | [19 empty] | 0
01-26-137 | Shell - NRM - WO#85476323 - Turbine Inspection | Shell Canada Products | T&M | [19 empty] | 0
01-26-125 | Shell - Pipe&Mech Support - PM-5154-REQ-004 | Shell Canada Products | FP | [19 empty] | 0
01-26-116 | Shell - Replace Inlet piping RV-1354 on FD-2 CAIR92276 | Shell Canada Products | FP | [19 empty] | 0
01-26-019 | Shell - Upgrade piping sections of 8â€ & 12â€-C789-SAG-5-IH (Shop) | Shell Canada Products | FP | [19 empty] | 0
01-26-201 | Shell - Utilities Piping Tie In for Little Dipper | Shell Canada Products | T&M | [19 empty] | 0
01-26-175 | Shell - WO#85434886 26GHT Pitstop - VLV1 - CAIR93112 | Shell Canada Products | FP | [19 empty] | 0
01-26-184 | Shell - WO#85465670 SP-510 Compressor outage | Shell Canada Products | T&M | [19 empty] | 0
01-26-179 | Shell - WO#85503067 CAIR93441 - Fabricate 12 New Elbow Spools for 2026 | Shell Canada Products | FP | [19 empty] | 0
01-26-154 | Shell - WO#85519051 26-NRM-Pipes in Mud | Shell Canada Products | T&M | [19 empty] | 0
01-26-178 | Shell - WO#85533830 Load AM-110 Salt Tower - DFL | Shell Canada Products | T&M | [19 empty] | 0
01-26-177 | Shell - WO#85533830 Load AM-110 Salt Tower - Overheads | Shell Canada Products | T&M | [19 empty] | 0
01-26-013 | Shell - WO#85538707 26NRM-COB- Purchase Stop CHE | Shell Canada Products | T&M | [19 empty] | 0
01-26-187 | Shell - WO#85539039 Effluent line hydrotest | Shell Canada Products | T&M | [19 empty] | 0
01-26-041 | Shell - WO#85557874 26BRINE-WOLVERINE-DFL | Shell Canada Products | T&M | [19 empty] | 0
01-26-043 | Shell - WO#85557874 26BRINE-WOLVERINE-OVERHEADS | Shell Canada Products | T&M | [19 empty] | 0
01-26-040 | Shell - WO#85557874CAIR-89773-Brine line replacement | Shell Canada Products | T&M | [19 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL FTE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Gould, Kyle
RESOURCE LOADING — Gould, Kyle
Enter FTE in the yellow cells. Leave Job # blank on the bottom rows to plan at client level.
Job # | Description | Client | Contract | Trade | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2027-01-02 | Total
01-26-053 | Shell - #WO85573750 25-NRM-Crude 2 Permanent Decon | Shell Canada Products | T&M | [19 empty] | 0
01-26-082 | Shell - 2026 - PEIM - Structural Inspection- Wol | Shell Canada Products | T&M | [19 empty] | 0
01-26-085 | Shell - 2026 - PEIM API 510 & API 570 Mitigation | Shell Canada Products | T&M | [19 empty] | 0
01-26-086 | Shell - 2026 Wolverine Planning Support | Shell Canada Products | T&M | [19 empty] | 0
01-26-084 | Shell - 2026-NRM-Pit Stop OHd's - Wolverine - Wo | Shell Canada Products | T&M | [19 empty] | 0
01-26-136 | Shell - 26CR3SPS - Mechanical - OPEX - Overheads | Shell Canada Products | T&M | [19 empty] | 0
01-26-146 | Shell - 26GHTPS - OPEX - DFL | Shell Canada Products | T&M | [19 empty] | 0
01-26-145 | Shell - 26GHTPS - OPEX - Overheads | Shell Canada Products | T&M | [19 empty] | 0
01-26-147 | Shell - 26UDXPS - OPEX - DFL | Shell Canada Products | T&M | [19 empty] | 0
01-26-148 | Shell - 26UDXPS - OPEX - Overheads | Shell Canada Products | T&M | [19 empty] | 0
01-26-143 | Shell - 3" #1500 Orbit Valve | Shell Canada Products | T&M | [19 empty] | 0
01-26-106 | Shell - 85406372 KF-7 - Full Internal Inspection – NRM-KF7 - OVERHEADS | Shell Canada Products | T&M | [19 empty] | 0
01-26-024 | Shell - 85470800 26SGB - V-3006 Dump/Reload - DFL | Shell Canada Products | T&M | [19 empty] | 0
01-26-026 | Shell - 85470800 26SGB - V-3006 Dump/Reload - Over Head | Shell Canada Products | T&M | [19 empty] | 0
01-26-039 | Shell - 85516723 26FCCUPS MOC-95239 Repair CB-101 BMS DFL | Shell Canada Products | T&M | [19 empty] | 0
01-26-052 | Shell - 85538707 26NRM-COB- Material Expedite | Shell Canada Products | T&M | [19 empty] | 0
01-26-034 | Shell - 85559406 26CR3R4PS - WLR# 2026-CR3-029 | Shell Canada Products | T&M | [19 empty] | 0
01-26-044 | Shell - 85570425 Weld metal build up SD-58 | Shell Canada Products | T&M | [19 empty] | 0
01-26-077 | Shell - WO# 84978727 - 24NRM – PUMP GP 57 | Shell Canada Products | T&M | [19 empty] | 0
01-26-133 | Shell - WO# 85462624 - P-4001B pump at chemical plant side | Shell Canada Products | T&M | [19 empty] | 0
01-26-163 | Shell - WO# 85462625 - SC-9 compressor at steam plant (PF/BM) | Shell Canada Products | T&M | [19 empty] | 0
01-26-078 | Shell - WO#85295544 - P-55 Pump overhaul MX07 | Shell Canada Products | T&M | [19 empty] | 0
01-26-064 | Shell - WO#85462632 2026 Corrosion Under Insulation - PF support | Shell Canada Products | T&M | [19 empty] | 0
01-26-190 | Shell - WO#85539281 Wolverine Planning Support 2026 | Shell Canada Products | T&M | [19 empty] | 0
01-26-181 | Shell - Wolverine onboarding | Shell Canada Products | T&M | [19 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL FTE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Jamer, Douglas
RESOURCE LOADING — Jamer, Douglas
Enter FTE in the yellow cells. Leave Job # blank on the bottom rows to plan at client level.
Job # | Description | Client | Contract | Trade | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2027-01-02 | Total
01-25-169 | CF - 2026TA - Pre-TA | CF Industries | T&M | [19 empty] | 0
01-25-177 | CF - Grade B engineering and installation - Boiler B-103 and Heater B- | CF Industries | T&M | [19 empty] | 0
01-26-038 | CF - Planning Support (01-25-217) - Ray Klassen | CF Industries | T&M | [19 empty] | 0
01-26-037 | CF - Project Controls Prior to TA | CF Industries | T&M | [19 empty] | 0
01-26-193 | CF - Wolverine Admin TA Support | CF Industries | T&M | [19 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL FTE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Kennedy, Michael
RESOURCE LOADING — Kennedy, Michael
Enter FTE in the yellow cells. Leave Job # blank on the bottom rows to plan at client level.
Job # | Description | Client | Contract | Trade | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2027-01-02 | Total
01-26-807 | CA - TA-UR-PP-010 4LT4010 Replace Drain Valve - 60011864 | CF Industries | T&M | [19 empty] | 0
01-26-808 | CA - TA-UR-PP-020 4LV4421 LPD Steam Valve - 60043519 | CF Industries | T&M | [19 empty] | 0
01-26-809 | CA - TA-UR-PP-021 4LV4441 Steam Out Valve - 60043540 | CF Industries | T&M | [19 empty] | 0
01-26-810 | CA - TA-UR-PP-022 Bar15 Steam Leak S3F3 - 60043542 | CF Industries | T&M | [19 empty] | 0
01-26-500 | CF - TA - A2 C110 Blowdown Line - 3 Work Orders Combined | CF Industries | T&M | [19 empty] | 0
01-26-503 | CF - TA-A2-PP-003 L301B RIK Corroded Nipple - 40012011 | CF Industries | T&M | [19 empty] | 0
01-26-502 | CF - TA-A2-PP-004 C405B RIK Corroded Pipe - 40012593 | CF Industries | T&M | [19 empty] | 0
01-26-504 | CF - TA-A2-PP-005 PSV2901 RIK Corroded Pipe - 40012609 | CF Industries | T&M | [19 empty] | 0
01-26-505 | CF - TA-A2-PP-006 RIK SW Pipe in Rack at D301- 40012654 | CF Industries | T&M | [19 empty] | 0
01-26-515 | CF - TA-A2-PP-007 LT5347 F501 RIK Corroded Nipple - 40012731 | CF Industries | T&M | [19 empty] | 0
01-26-506 | CF - TA-A2-PP-008 8PV1752 RIK Upstream BW Valve - 60009389 | CF Industries | T&M | [19 empty] | 0
01-26-516 | CF - TA-A2-PP-018 F401 Replace VLVs to F501 - 60009798 | CF Industries | T&M | [19 empty] | 0
01-26-507 | CF - TA-A2-PP-023 8LV3115 Repair Strainer - 60010344 | CF Industries | T&M | [19 empty] | 0
01-26-517 | CF - TA-A2-PP-031 HV1072 Replace Drain Vlvs - 60015209 | CF Industries | T&M | [19 empty] | 0
01-26-522 | CF - TA-A2-PP-032 ROB5528 Replace Drain Vlvs - 60015210 | CF Industries | T&M | [19 empty] | 0
01-26-525 | CF - TA-A2-PP-034 B102 Repair BFW Pipe - 60015256 | CF Industries | T&M | [19 empty] | 0
01-26-531 | CF - TA-A2-PP-036 J101-7AB Replace Equal Vlv - 60010915 | CF Industries | T&M | [19 empty] | 0
01-26-526 | CF - TA-A2-PP-040 G404 LGs Install Caps - 60010048 | CF Industries | T&M | [19 empty] | 0
01-26-527 | CF - TA-A2-PP-041 D301 Outlet Bleed Valve - 60043511 | CF Industries | T&M | [19 empty] | 0
01-26-528 | CF - TA-A2-PP-042 FV4144 Drain Valves - 60043512 | CF Industries | T&M | [19 empty] | 0
01-26-532 | CF - TA-A2-PP-044 E24-118 Decommission UG CO2 Line | CF Industries | T&M | [19 empty] | 0
01-26-533 | CF - TA-A2-PP-045 E24-213 J101 Eliminate Low Point - 20000606 | CF Industries | T&M | [19 empty] | 0
01-26-600 | CF - TA-DS-PP-002 LV2101 CUI Pipe RIK - 40012600 | CF Industries | T&M | [19 empty] | 0
01-26-601 | CF - TA-DS-PP-003 3-LAA-54 CUI Pipe RIK - 40012596 | CF Industries | T&M | [19 empty] | 0
01-26-602 | CF - TA-DS-PP-005 2-LAA-48 CUI Pipe RIK - 40012605 | CF Industries | T&M | [19 empty] | 0
01-26-603 | CF - TA-DS-PP-007 14-LAE-22006 Vent 1 CUI RIK - 40012611 | CF Industries | T&M | [19 empty] | 0
01-26-604 | CF - TA-DS-PP-008 14-LAE-22006 Vent 2 CUI RIK - 40012614 | CF Industries | T&M | [19 empty] | 0
01-26-700 | CF - TA-NI-PP-001 3E107 Boot Drain Vlv RIK - 60009546 | CF Industries | T&M | [19 empty] | 0
01-26-701 | CF - TA-NI-PP-002 P2B Replace BD Valve - 60010876 | CF Industries | T&M | [19 empty] | 0
01-26-508 | CF - TA-OLLR-A2-PP-001 PSV-1903 Remove Encl - 40011635 | CF Industries | T&M | [19 empty] | 0
01-26-529 | CF - TA-OLLR-A2-PP-010 200# Steam Remove Encl - 60009556 | CF Industries | T&M | [19 empty] | 0
01-26-518 | CF - TA-OLLR-A2-PP-014 LV5178 Remove Encl - 60009691 | CF Industries | T&M | [19 empty] | 0
01-26-519 | CF - TA-OLLR-A2-PP-016 TV1068 Remove Encl - 60009696 | CF Industries | T&M | [19 empty] | 0
01-26-510 | CF - TA-OLLR-A2-PP-017 CML11 Remove Encl - 60009698 | CF Industries | T&M | [19 empty] | 0
01-26-509 | CF - TA-OLLR-A2-PP-020 PV1061A Remove 2x Encl - 60010008 | CF Industries | T&M | [19 empty] | 0
01-26-512 | CF - TA-OLLR-A2-PP-021 TV1064 Remove Encl - 60010064 | CF Industries | T&M | [19 empty] | 0
01-26-520 | CF - TA-OLLR-A2-PP-022 C115 Remove Enclosure - 60010066 | CF Industries | T&M | [19 empty] | 0
01-26-514 | CF - TA-OLLR-A2-PP-027 HV1623 Remove Encl - 60010738 | CF Industries | T&M | [19 empty] | 0
01-26-521 | CF - TA-OLLR-A2-PP-028 J107-C128 Replace Pipe - 60010920 | CF Industries | T&M | [19 empty] | 0
01-26-523 | CF - TA-OLLR-A2-PP-030 8FV4140 Byps Drain Vlv - 60015207 | CF Industries | T&M | [19 empty] | 0
01-26-524 | CF - TA-OLLR-A2-PP-033 L501 Repair Steam Trap - 60015223 | CF Industries | T&M | [19 empty] | 0
01-26-530 | CF - TA-OLLR-A2-PP-043 - C501 Perm Piping Repair | CF Industries | T&M | [19 empty] | 0
01-26-537 | CF - TA-OLLR-A2-PP-049 C109 Drain Valves - 60010923 | CF Industries | T&M | [19 empty] | 0
01-26-538 | CF - TA-OLLR-A2-VLV-012 TV1068 Remove Encl - 60010068 | CF Industries | T&M | [19 empty] | 0
01-26-805 | CF - TA-TMOC-UR-PP-012 4PCV895 Outlet PI - 20000745 | CF Industries | T&M | [19 empty] | 0
01-26-800 | CF - TA-UR-PP-004 E121 Replace Drain Valve - 60009998 | CF Industries | T&M | [19 empty] | 0
01-26-803 | CF - TA-UR-PP-005 P117B Xmas Tree Drain Vlv - 60010150 | CF Industries | T&M | [19 empty] | 0
01-26-801 | CF - TA-UR-PP-008 P5A LPFW Replace Valve - 60010635 | CF Industries | T&M | [19 empty] | 0
01-26-804 | CF - TA-UR-PP-009 CM10 Repair Steam Leak - 60010637 | CF Industries | T&M | [19 empty] | 0
01-26-806 | CF - TA-UR-PP-011 T1 Replace LPFW Valves - 60013439 | CF Industries | T&M | [19 empty] | 0
01-25-149 | Cope Const. - Cando Rail Expansion | Cope Construction Co | FP | [19 empty] | 0
01-26-168 | IOL - COB TA – WPR-011 Machining | Imperial Oil | T&M | [19 empty] | 0
01-26-150 | IOL - S2-E-2201 North Channel Machining | Imperial Oil | T&M | [19 empty] | 0
01-26-534 | TA-A2-PP-046 A3F5 E404A Drain Valve - 60048960 | CF Industries | T&M | [19 empty] | 0
01-26-535 | TA-A2-PP-047 XV4629 Replace Bypass Valve - 60010508 | CF Industries | T&M | [19 empty] | 0
01-26-536 | TA-A2-VLV-018 PCV4617 RIK Reg Pipe Flange - 60011044 | CF Industries | T&M | [19 empty] | 0
01-26-513 | TA-OLLR-A2-PP-024 8PV3095 Replace Block Vlv- 60010420 | CF Industries | T&M | [19 empty] | 0
01-26-812 | TA-UR-PP-019 Repair Double Block and Bleed - 60010675 | CF Industries | T&M | [19 empty] | 0
01-26-094 | TKO - Kingston Line Stop Support | TKO Industrial Services Corporation | T&M | [19 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL FTE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Kennedy, Vince
RESOURCE LOADING — Kennedy, Vince
Enter FTE in the yellow cells. Leave Job # blank on the bottom rows to plan at client level.
Job # | Description | Client | Contract | Trade | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2027-01-02 | Total
01-26-189 | IOL - Install new gelcoat on six existing Biox Clarifier floats | Imperial Oil | T&M | [19 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL FTE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Morningstar, Jeremy J
RESOURCE LOADING — Morningstar, Jeremy J
Enter FTE in the yellow cells. Leave Job # blank on the bottom rows to plan at client level.
Job # | Description | Client | Contract | Trade | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2027-01-02 | Total
02-26-011 | Arlanxeo - ESR-2025-0170 – Remove V3 at SWPH | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-25-031 | ITS - Tank 865 Berm Assessment | Interface Testing Services Inc | FP | [19 empty] | 0
02-26-008 | Nova Rokeby - laser scanning - Rokeby Site | Nova Chemicals Corporation | FP | [19 empty] | 0
02-25-004 | Suncor - Safety Incident Scanning (1000:0010600132) | Suncor Energy Inc | T&M | [19 empty] | 0
02-26-016 | Suncor - Tank High Level Verification – Fixed Roof Tanks | Suncor Energy Inc | FP | [19 empty] | 0
02-26-019 | VIP - Warehouse Buildings | VIP Rail | FP | [19 empty] | 0
02-26-025 | W-ENG - MOC 94232 CR2 - KC-4-EX - Detailed Engineering | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-26-024 | W-ENG - MOC 95449 CR2 - 2Crude- KCC15 - Detailed Engineering | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-26-023 | W-ENG - MOC 95479 GHT - NPV321 - Detailed Engineering | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-26-022 | W-ENG - MOC 95881 CR2 - KB-1-C-FUR - Detailed Engineering | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-26-021 | W-ENG - MOC 96026 CR2 - 2Crude-KCC17 - Detailed Engineering | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-26-020 | W-ENG - MOC 96028 CR2 - KC-20A-EX - Detailed Engineering | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-26-030 | WLV-ENG - FCM EA-2125a Add Tie-Points | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-26-035 | WLV-ENG - FCM MO Deaerator COTA27 Piping Scope | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-26-027 | WLV-ENG - FCM ROTA CW Carrier Water Tie Points | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-26-028 | WLV-ENG - FCM ROTA Demo Extruder Room HP Steam Cond Manifold | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-26-029 | WLV-ENG - FCM ROTA Install Flush or N2 on Photo Eye | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-26-031 | WLV-ENG - FCM ROTA Install PSV0083 Drain Valves | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-26-032 | WLV-ENG - FCM ROTA Install PSV3660 Drain Valve | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-26-034 | WLV-ENG - FCM ROTA J Compressor CW Isolation and Bypass | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-26-026 | WLV-ENG - FCM ROTA Refrig Isolation Improvements | Wolverine Engineering Ltd. | FP | [19 empty] | 0
02-26-033 | WLV-ENG - FCM ROTA SAT Ext TW Manifold Isolation Valve | Wolverine Engineering Ltd. | FP | [19 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL FTE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Pendlebury, Jay
RESOURCE LOADING — Pendlebury, Jay
Enter FTE in the yellow cells. Leave Job # blank on the bottom rows to plan at client level.
Job # | Description | Client | Contract | Trade | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2027-01-02 | Total
01-25-128 | Enbridge - refrigerant line - Hagar | Enbridge Gas Inc | FP | [19 empty] | 0
01-24-085 | Enbridge: Fabricate & install 1" pipe to tie-in point at Parkway | Enbridge Gas Inc | FP | [19 empty] | 0
01-25-140 | H.C. Starck - Kiln 1 Exhaust Header Replacement | H.C. Starck Canada Inc. | T&M | [19 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL FTE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Poore, Jordan
RESOURCE LOADING — Poore, Jordan
Enter FTE in the yellow cells. Leave Job # blank on the bottom rows to plan at client level.
Job # | Description | Client | Contract | Trade | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2027-01-02 | Total
01-25-171 | Ainsworth - QC Support for Ainsworth | Ainsworth Technical LP | T&M | [19 empty] | 0
01-25-022 | Arlanxeo - 2025 Arlanxeo WPS Development | Arlanxeo Canada Inc. | T&M | [19 empty] | 0
01-26-200 | CF - QA/QC Planner for fall TA | CF Industries | T&M | [19 empty] | 0
01-25-137 | Wolverine - Nuclear Certification | Wolverine Engineering Ltd. | T&M | [19 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL FTE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Powers, Dave
RESOURCE LOADING — Powers, Dave
Enter FTE in the yellow cells. Leave Job # blank on the bottom rows to plan at client level.
Job # | Description | Client | Contract | Trade | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2027-01-02 | Total
01-25-129 | Diamond - BOILERMAKER SUPPORT-DPCC MAINTENANCE | Diamond Petrochemicals Canada | T&M | [19 empty] | 0
01-26-058 | DOW - MA Tank Vent Extension | Dow Chemical Canada Inc | T&M | [19 empty] | 0
01-26-023 | DPCC - 03-26018 - HPIB SAVINGS | Diamond Petrochemicals Canada | FP | [19 empty] | 0
01-26-059 | DPCC - D-57 VESSEL REPLACEMENT | Diamond Petrochemicals Canada | FP | [19 empty] | 0
01-26-203 | DPCC - Sept Cleaning outage BM work | Diamond Petrochemicals Canada | T&M | [19 empty] | 0
01-26-204 | DPCC - T 40 Platform Install | Diamond Petrochemicals Canada | T&M | [19 empty] | 0
01-26-185 | DPCC - T-40 Platforms And Ladders, DI-24-001, Civil / Structural – CWP | Diamond Petrochemicals Canada | FP | [19 empty] | 0
01-26-122 | Enbridge - TBD1 - PO#4950037827 | Enbridge Gas Inc | T&M | [19 empty] | 0
01-26-123 | Enbridge - TBD2 - PO#4950037207 | Enbridge Gas Inc | T&M | [19 empty] | 0
01-26-124 | Enbridge - TBD3 - PO#4950037426 | Enbridge Gas Inc | T&M | [19 empty] | 0
01-25-001 | H. C. Starck - Insulation Services | H.C. Starck Canada Inc. | T&M | [19 empty] | 0
01-25-234 | H. C. Starck - Insulation Services 2026 | H.C. Starck Canada Inc. | T&M | [19 empty] | 0
01-26-049 | H. C. Starck Canada - Kiln 1 Drier Upgrade | H.C. Starck Canada Inc. | T&M | [19 empty] | 0
01-25-002 | H.C.Starck – Pipefitting Services | H.C. Starck Canada Inc. | T&M | [19 empty] | 0
01-25-235 | H.C.Starck – Pipefitting Services | H.C. Starck Canada Inc. | T&M | [19 empty] | 0
01-26-017 | Hydrostor - PSV Removal and delivery | Hydrostor | T&M | [19 empty] | 0
01-26-095 | MN Mechanical - Asbestos on water drains | MN Mechanical | T&M | [19 empty] | 0
01-26-018 | MN Mechanical - Asbestos remediation in Maintenance garage | MN Mechanical | T&M | [19 empty] | 0
01-26-046 | Nova Rokeby - ROTA27 Wolverine Management | Nova Chemicals Corporation | T&M | [19 empty] | 0
01-25-226 | Suncor - 2026 - Kim Daborn - Safety Support | Suncor Energy Inc | T&M | [19 empty] | 0
01-26-032 | Suncor - 2026 Marc Jolicoeur Planning Support | Suncor Energy Inc | T&M | [19 empty] | 0
01-25-198 | Suncor - 2027 TA Spring TA Planning Support | Suncor Energy Inc | T&M | [19 empty] | 0
01-25-200 | Suncor - 2028 TA Planning Support | Suncor Energy Inc | T&M | [19 empty] | 0
01-26-167 | Suncor - the Cooling Water Line Upgrade Piping | Suncor Energy Inc | FP | [19 empty] | 0
01-26-093 | Suncor Ethanol - Piping and Insulation Services - Distillation & Dehy | Suncor Energy Inc | T&M | [19 empty] | 0
01-26-114 | Suncor Ethanol - Ferm Exchanger piping | Suncor Energy Inc | T&M | [19 empty] | 0
01-25-228 | Suncor Ethanol - Wolverine 2026 Call in support | Suncor Energy Inc | T&M | [19 empty] | 0
01-25-205 | University of Guelph - 2025-26 Insulation Improvements (Proj. # 621386 | University of Guelph | T&M | [19 empty] | 0
01-26-089 | University of Guelph - Insulation on Exposed Ductwork | University of Guelph | FP | [19 empty] | 0
01-26-195 | Wolverine Eng. - ASME FLANGED AND DISHED 96" OD HEAD - conrex steel | Wolverine Engineering Ltd. | FP | [19 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL FTE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Lists
Trades | Clients | Project Managers
Boilermaker | Aecon Industrial | Barrett, Ken
Pipefitter / Steamfitter | Ainsworth Technical LP | Brundage, Eric
Welder | Arlanxeo Canada Inc. | Dubois, Joe
Millwright | CF Industries | Gould, Kyle
Ironworker | Cope Construction Co | Jamer, Douglas
Electrician | Diamond Petrochemicals Canada | Kennedy, Michael
Instrumentation | Dow Chemical Canada Inc | Kennedy, Vince
Insulator | Enbridge Gas Inc | Morningstar, Jeremy J
Scaffolder | Goodfellow Construction (1993) Ltd. | Pendlebury, Jay
Labourer | H.C. Starck Canada Inc. | Poore, Jordan
Crane Operator / Rigger | Hydrostor | Powers, Dave
QA / QC | Imperial Oil
Supervision | Interface Testing Services Inc
Project Management | MN Mechanical
Engineering / Design | Nova Chemicals Corporation
Drafting / Modelling | Shell Canada Products
Safety | Suncor Energy Inc
TKO Industrial Services Corporation
Add trades here — dropdowns and the Trade summary follow this list. | TransAlta (SC) LP
University of Guelph
VIP Rail
Wolverine Engineering Ltd.

## Input - Project List
Job # | Description | Client | PM | Contract | Job Type | Status
04-26-001 | AECON - CEPPS Modularization | Aecon Industrial | Barrett, Ken | T&M | 04 - Nuclear | Active
04-26-002 | AECON - TBM Pipe Basket - Darlington SMR | Aecon Industrial | Barrett, Ken | T&M | 04 - Nuclear | Active
01-26-099 | Nova - C9200 LEAK | Nova Chemicals Corporation | Barrett, Ken | FP | 01 - Industrial | Active
01-26-097 | Boiler 128 Ductwork Baffles | Nova Chemicals Corporation | Brundage, Eric | T&M | 01 - Industrial | Active
01-26-045 | Nova Corunna - 28950 – Piping Demolition | Nova Chemicals Corporation | Brundage, Eric | T&M | 01 - Industrial | Active
01-26-020 | Nova Corunna - Heater BA-2107 TLEs & Coils | Nova Chemicals Corporation | Brundage, Eric | T&M | 01 - Industrial | Active
01-26-149 | Nova Corunna - Quench Header EPC | Nova Chemicals Corporation | Brundage, Eric | T&M | 01 - Industrial | Active
01-26-152 | Nova Corunna - Wolverine - 29307 - Heater Tie-Ins | Nova Chemicals Corporation | Brundage, Eric | T&M | 01 - Industrial | Active
01-26-182 | Nova Moore - FCM Y-527 and Piping Replacement | Nova Chemicals Corporation | Brundage, Eric | T&M | 01 - Industrial | Active
01-24-334 | NOVA Moore - MENox Compliance | Nova Chemicals Corporation | Brundage, Eric | FP | 01 - Industrial | Active
01-26-144 | Suncor Ethanol - #300664881 - 2026 Annual - Ethanol Plant Call in Support – Wolverine | Suncor Energy Inc | Brundage, Eric | T&M | 01 - Industrial | Active
01-26-100 | Suncor Ethanol - CIP Light Phase Piping | Suncor Energy Inc | Brundage, Eric | T&M | 01 - Industrial | Active
01-26-009 | TransAlta - Superheater Drains | TransAlta (SC) LP | Brundage, Eric | T&M | 01 - Industrial | Active
01-26-092 | TransAlta - TAN 420 Steam Tie-Ins | TransAlta (SC) LP | Brundage, Eric | T&M | 01 - Industrial | Active
01-26-121 | GoodFellow - Install & Fab Support at Pembina(A6012.01-8B-00224&00223) | Goodfellow Construction (1993) Ltd. | Dubois, Joe | FP | 01 - Industrial | Active
01-26-111 | Shell - 26FCCUPS - OPEX - DFL | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-112 | Shell - 26FCCUPS - OPEX - Overheads | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-166 | Shell - WO#85445251 New Replacement ATI-31 MOC-95468 - OVERHEADS | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-080 | Shell - 2026 NRM-Crude 2 exchangers- Wolverine | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-079 | Shell - 26 NRM CUI CWP-47A FCCU-CE101R Capex- Wo | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-138 | Shell - 26CR3SPS- Mechanical - OPEX - DFL | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-156 | Shell - 26FCCUPS - Replace CF - 222 drain piping | Shell Canada Products | Dubois, Joe | FP | 01 - Industrial | Active
01-26-010 | Shell - 26NRM-CC-309R-bundle repair - DFL | Shell Canada Products | Dubois, Joe | T&M | 01 - Project | Active
01-26-197 | Shell - 5103-Piping-CPK | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-188 | Shell - 5116-PROJ-LITTLE DIPPER SUPPORT | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-170 | Shell - 5148 Flare Gas SO2 Minimization – Phase 2 | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-169 | Shell - 5148 Flare Gas SO2 Minimization – Phase 2 (Fab) | Shell Canada Products | Dubois, Joe | FP | 01 - Industrial | Active
01-26-021 | Shell - 5169-PROJ-MiscWork-RailCapPh2 | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-066 | Shell - 85406372 KF-7 - Full Internal Inspection – NRM-KF7 - DFL | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-051 | Shell - 85407798 2025 NRM - Jet line to Tank 8 Capex | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-096 | Shell - Aeration Basin MOC Phase 1-6 | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-118 | Shell - CAIR91467-GHT RPLC Steam Drain valve | Shell Canada Products | Dubois, Joe | FP | 01 - Industrial | Active
01-26-098 | Shell - CAIR-93408-MOC95448-CPV153 | Shell Canada Products | Dubois, Joe | FP | 01 - Industrial | Active
01-26-055 | Shell - CAIR-93571-CE-310R-Caustic ppg | Shell Canada Products | Dubois, Joe | FP | 01 - Industrial | Active
01-26-120 | Shell - CR3/Regen Lube Oil piping CAIR000093748 | Shell Canada Products | Dubois, Joe | FP | 01 - Industrial | Active
01-26-090 | Shell - Demo CC-218, CC-219, CC-220 | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-091 | Shell - Fabricate CAIR93581-MOC97688-KFT244 Replacement | Shell Canada Products | Dubois, Joe | FP | 01 - Industrial | Active
01-26-202 | Shell - Install 1500 ft of 4â€ Soybean Oil piping | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-056 | Shell - maintenance support 2026 #85485360 | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-131 | Shell - NRM - WO#85263243 - Pump Removal | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-137 | Shell - NRM - WO#85476323 - Turbine Inspection | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-125 | Shell - Pipe&Mech Support - PM-5154-REQ-004 | Shell Canada Products | Dubois, Joe | FP | 01 - Industrial | Active
01-26-116 | Shell - Replace Inlet piping RV-1354 on FD-2 CAIR92276 | Shell Canada Products | Dubois, Joe | FP | 01 - Industrial | Active
01-26-019 | Shell - Upgrade piping sections of 8â€ & 12â€-C789-SAG-5-IH (Shop) | Shell Canada Products | Dubois, Joe | FP | 01 - Industrial | Active
01-26-201 | Shell - Utilities Piping Tie In for Little Dipper | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-175 | Shell - WO#85434886 26GHT Pitstop - VLV1 - CAIR93112 | Shell Canada Products | Dubois, Joe | FP | 01 - Industrial | Active
01-26-184 | Shell - WO#85465670 SP-510 Compressor outage | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-179 | Shell - WO#85503067 CAIR93441 - Fabricate 12 New Elbow Spools for 2026 FCCU | Shell Canada Products | Dubois, Joe | FP | 01 - Industrial | Active
01-26-154 | Shell - WO#85519051 26-NRM-Pipes in Mud | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-178 | Shell - WO#85533830 Load AM-110 Salt Tower - DFL | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-177 | Shell - WO#85533830 Load AM-110 Salt Tower - Overheads | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-013 | Shell - WO#85538707 26NRM-COB- Purchase Stop CHE | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-187 | Shell - WO#85539039 Effluent line hydrotest | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-041 | Shell - WO#85557874 26BRINE-WOLVERINE-DFL | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-043 | Shell - WO#85557874 26BRINE-WOLVERINE-OVERHEADS | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-040 | Shell - WO#85557874CAIR-89773-Brine line replacement | Shell Canada Products | Dubois, Joe | T&M | 01 - Industrial | Active
01-26-053 | Shell - #WO85573750 25-NRM-Crude 2 Permanent Decon | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-082 | Shell - 2026 - PEIM - Structural Inspection- Wol | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-085 | Shell - 2026 - PEIM API 510 & API 570 Mitigation | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-086 | Shell - 2026 Wolverine Planning Support | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-084 | Shell - 2026-NRM-Pit Stop OHd's - Wolverine - Wo | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-136 | Shell - 26CR3SPS - Mechanical - OPEX - Overheads | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-146 | Shell - 26GHTPS - OPEX - DFL | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-145 | Shell - 26GHTPS - OPEX - Overheads | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-147 | Shell - 26UDXPS - OPEX - DFL | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-148 | Shell - 26UDXPS - OPEX - Overheads | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-143 | Shell - 3" #1500 Orbit Valve | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-106 | Shell - 85406372 KF-7 - Full Internal Inspection – NRM-KF7 - OVERHEADS | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-024 | Shell - 85470800 26SGB - V-3006 Dump/Reload - DFL | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-026 | Shell - 85470800 26SGB - V-3006 Dump/Reload - Over Head | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-039 | Shell - 85516723 26FCCUPS MOC-95239 Repair CB-101 BMS DFL | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-052 | Shell - 85538707 26NRM-COB- Material Expedite | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-034 | Shell - 85559406 26CR3R4PS - WLR# 2026-CR3-029 | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-044 | Shell - 85570425 Weld metal build up SD-58 | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-077 | Shell - WO# 84978727 - 24NRM – PUMP GP 57 | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-133 | Shell - WO# 85462624 - P-4001B pump at chemical plant side | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-163 | Shell - WO# 85462625 - SC-9 compressor at steam plant (PF/BM) | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-078 | Shell - WO#85295544 - P-55 Pump overhaul MX07 | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-064 | Shell - WO#85462632 2026 Corrosion Under Insulation - PF support | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-190 | Shell - WO#85539281 Wolverine Planning Support 2026 | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-26-181 | Shell - Wolverine onboarding | Shell Canada Products | Gould, Kyle | T&M | 01 - Industrial | Active
01-25-169 | CF - 2026TA - Pre-TA | CF Industries | Jamer, Douglas | T&M | 01 - Industrial | Active
01-25-177 | CF - Grade B engineering and installation - Boiler B-103 and Heater B-401. | CF Industries | Jamer, Douglas | T&M | 01 - Industrial | Active
01-26-038 | CF - Planning Support (01-25-217) - Ray Klassen | CF Industries | Jamer, Douglas | T&M | 01 - Industrial | Active
01-26-037 | CF - Project Controls Prior to TA | CF Industries | Jamer, Douglas | T&M | 01 - Industrial | Active
01-26-193 | CF - Wolverine Admin TA Support | CF Industries | Jamer, Douglas | T&M | 01 - Industrial | Active
01-26-807 | CA - TA-UR-PP-010 4LT4010 Replace Drain Valve - 60011864 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-808 | CA - TA-UR-PP-020 4LV4421 LPD Steam Valve - 60043519 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-809 | CA - TA-UR-PP-021 4LV4441 Steam Out Valve - 60043540 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-810 | CA - TA-UR-PP-022 Bar15 Steam Leak S3F3 - 60043542 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-500 | CF - TA - A2 C110 Blowdown Line - 3 Work Orders Combined | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-503 | CF - TA-A2-PP-003 L301B RIK Corroded Nipple - 40012011 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-502 | CF - TA-A2-PP-004 C405B RIK Corroded Pipe - 40012593 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-504 | CF - TA-A2-PP-005 PSV2901 RIK Corroded Pipe - 40012609 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-505 | CF - TA-A2-PP-006 RIK SW Pipe in Rack at D301- 40012654 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-515 | CF - TA-A2-PP-007 LT5347 F501 RIK Corroded Nipple - 40012731 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-506 | CF - TA-A2-PP-008 8PV1752 RIK Upstream BW Valve - 60009389 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-516 | CF - TA-A2-PP-018 F401 Replace VLVs to F501 - 60009798 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-507 | CF - TA-A2-PP-023 8LV3115 Repair Strainer - 60010344 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-517 | CF - TA-A2-PP-031 HV1072 Replace Drain Vlvs - 60015209 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-522 | CF - TA-A2-PP-032 ROB5528 Replace Drain Vlvs - 60015210 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-525 | CF - TA-A2-PP-034 B102 Repair BFW Pipe - 60015256 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-531 | CF - TA-A2-PP-036 J101-7AB Replace Equal Vlv - 60010915 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-526 | CF - TA-A2-PP-040 G404 LGs Install Caps - 60010048 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-527 | CF - TA-A2-PP-041 D301 Outlet Bleed Valve - 60043511 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-528 | CF - TA-A2-PP-042 FV4144 Drain Valves - 60043512 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-532 | CF - TA-A2-PP-044 E24-118 Decommission UG CO2 Line | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-533 | CF - TA-A2-PP-045 E24-213 J101 Eliminate Low Point - 20000606 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-600 | CF - TA-DS-PP-002 LV2101 CUI Pipe RIK - 40012600 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-601 | CF - TA-DS-PP-003 3-LAA-54 CUI Pipe RIK - 40012596 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-602 | CF - TA-DS-PP-005 2-LAA-48 CUI Pipe RIK - 40012605 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-603 | CF - TA-DS-PP-007 14-LAE-22006 Vent 1 CUI RIK - 40012611 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-604 | CF - TA-DS-PP-008 14-LAE-22006 Vent 2 CUI RIK - 40012614 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-700 | CF - TA-NI-PP-001 3E107 Boot Drain Vlv RIK - 60009546 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-701 | CF - TA-NI-PP-002 P2B Replace BD Valve - 60010876 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-508 | CF - TA-OLLR-A2-PP-001 PSV-1903 Remove Encl - 40011635 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-529 | CF - TA-OLLR-A2-PP-010 200# Steam Remove Encl - 60009556 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-518 | CF - TA-OLLR-A2-PP-014 LV5178 Remove Encl - 60009691 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-519 | CF - TA-OLLR-A2-PP-016 TV1068 Remove Encl - 60009696 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-510 | CF - TA-OLLR-A2-PP-017 CML11 Remove Encl - 60009698 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-509 | CF - TA-OLLR-A2-PP-020 PV1061A Remove 2x Encl - 60010008 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-512 | CF - TA-OLLR-A2-PP-021 TV1064 Remove Encl - 60010064 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-520 | CF - TA-OLLR-A2-PP-022 C115 Remove Enclosure - 60010066 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-514 | CF - TA-OLLR-A2-PP-027 HV1623 Remove Encl - 60010738 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-521 | CF - TA-OLLR-A2-PP-028 J107-C128 Replace Pipe - 60010920 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-523 | CF - TA-OLLR-A2-PP-030 8FV4140 Byps Drain Vlv - 60015207 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-524 | CF - TA-OLLR-A2-PP-033 L501 Repair Steam Trap - 60015223 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-530 | CF - TA-OLLR-A2-PP-043 - C501 Perm Piping Repair | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-537 | CF - TA-OLLR-A2-PP-049 C109 Drain Valves - 60010923 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-538 | CF - TA-OLLR-A2-VLV-012 TV1068 Remove Encl - 60010068 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-805 | CF - TA-TMOC-UR-PP-012 4PCV895 Outlet PI - 20000745 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-800 | CF - TA-UR-PP-004 E121 Replace Drain Valve - 60009998 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-803 | CF - TA-UR-PP-005 P117B Xmas Tree Drain Vlv - 60010150 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-801 | CF - TA-UR-PP-008 P5A LPFW Replace Valve - 60010635 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-804 | CF - TA-UR-PP-009 CM10 Repair Steam Leak - 60010637 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-806 | CF - TA-UR-PP-011 T1 Replace LPFW Valves - 60013439 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-25-149 | Cope Const. - Cando Rail Expansion | Cope Construction Co | Kennedy, Michael | FP | 01 - Industrial | Active
01-26-168 | IOL - COB TA – WPR-011 Machining | Imperial Oil | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-150 | IOL - S2-E-2201 North Channel Machining | Imperial Oil | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-534 | TA-A2-PP-046 A3F5 E404A Drain Valve - 60048960 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-535 | TA-A2-PP-047 XV4629 Replace Bypass Valve - 60010508 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-536 | TA-A2-VLV-018 PCV4617 RIK Reg Pipe Flange - 60011044 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-513 | TA-OLLR-A2-PP-024 8PV3095 Replace Block Vlv- 60010420 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-812 | TA-UR-PP-019 Repair Double Block and Bleed - 60010675 | CF Industries | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-094 | TKO - Kingston Line Stop Support | TKO Industrial Services Corporation | Kennedy, Michael | T&M | 01 - Industrial | Active
01-26-189 | IOL - Install new gelcoat on six existing Biox Clarifier floats | Imperial Oil | Kennedy, Vince | T&M | 01 - Industrial | Active
02-26-011 | Arlanxeo - ESR-2025-0170 – Remove V3 at SWPH | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-25-031 | ITS - Tank 865 Berm Assessment | Interface Testing Services Inc | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-008 | Nova Rokeby - laser scanning - Rokeby Site | Nova Chemicals Corporation | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-25-004 | Suncor - Safety Incident Scanning (1000:0010600132) | Suncor Energy Inc | Morningstar, Jeremy J | T&M | 02 - 3D Scanning | Active
02-26-016 | Suncor - Tank High Level Verification – Fixed Roof Tanks | Suncor Energy Inc | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-019 | VIP - Warehouse Buildings | VIP Rail | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-025 | W-ENG - MOC 94232 CR2 - KC-4-EX - Detailed Engineering | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-024 | W-ENG - MOC 95449 CR2 - 2Crude- KCC15 - Detailed Engineering | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-023 | W-ENG - MOC 95479 GHT - NPV321 - Detailed Engineering | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-022 | W-ENG - MOC 95881 CR2 - KB-1-C-FUR - Detailed Engineering | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-021 | W-ENG - MOC 96026 CR2 - 2Crude-KCC17 - Detailed Engineering | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-020 | W-ENG - MOC 96028 CR2 - KC-20A-EX - Detailed Engineering | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-030 | WLV-ENG - FCM EA-2125a Add Tie-Points | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-035 | WLV-ENG - FCM MO Deaerator COTA27 Piping Scope | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-027 | WLV-ENG - FCM ROTA CW Carrier Water Tie Points | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-028 | WLV-ENG - FCM ROTA Demo Extruder Room HP Steam Cond Manifold | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-029 | WLV-ENG - FCM ROTA Install Flush or N2 on Photo Eye | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-031 | WLV-ENG - FCM ROTA Install PSV0083 Drain Valves | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-032 | WLV-ENG - FCM ROTA Install PSV3660 Drain Valve | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-034 | WLV-ENG - FCM ROTA J Compressor CW Isolation and Bypass | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-026 | WLV-ENG - FCM ROTA Refrig Isolation Improvements | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
02-26-033 | WLV-ENG - FCM ROTA SAT Ext TW Manifold Isolation Valve | Wolverine Engineering Ltd. | Morningstar, Jeremy J | FP | 02 - 3D Scanning | Active
01-25-128 | Enbridge - refrigerant line - Hagar | Enbridge Gas Inc | Pendlebury, Jay | FP | 01 - Industrial | Active
01-24-085 | Enbridge: Fabricate & install 1" pipe to tie-in point at Parkway | Enbridge Gas Inc | Pendlebury, Jay | FP | 01 - Industrial | Active
01-25-140 | H.C. Starck - Kiln 1 Exhaust Header Replacement | H.C. Starck Canada Inc. | Pendlebury, Jay | T&M | 01 - Industrial | Active
01-25-171 | Ainsworth - QC Support for Ainsworth | Ainsworth Technical LP | Poore, Jordan | T&M | 01 - Industrial | Active
01-25-022 | Arlanxeo - 2025 Arlanxeo WPS Development | Arlanxeo Canada Inc. | Poore, Jordan | T&M | 01 - Industrial | Active
01-26-200 | CF - QA/QC Planner for fall TA | CF Industries | Poore, Jordan | T&M | 01 - Industrial | Active
01-25-137 | Wolverine - Nuclear Certification | Wolverine Engineering Ltd. | Poore, Jordan | T&M | 01 - Industrial | Active
01-25-129 | Diamond - BOILERMAKER SUPPORT-DPCC MAINTENANCE | Diamond Petrochemicals Canada | Powers, Dave | T&M | 01 - Industrial | Active
01-26-058 | DOW - MA Tank Vent Extension | Dow Chemical Canada Inc | Powers, Dave | T&M | 01 - Industrial | Active
01-26-023 | DPCC - 03-26018 - HPIB SAVINGS | Diamond Petrochemicals Canada | Powers, Dave | FP | 01 - Industrial | Active
01-26-059 | DPCC - D-57 VESSEL REPLACEMENT | Diamond Petrochemicals Canada | Powers, Dave | FP | 01 - Industrial | Active
01-26-203 | DPCC - Sept Cleaning outage BM work | Diamond Petrochemicals Canada | Powers, Dave | T&M | 01 - Industrial | Active
01-26-204 | DPCC - T 40 Platform Install | Diamond Petrochemicals Canada | Powers, Dave | T&M | 01 - Industrial | Active
01-26-185 | DPCC - T-40 Platforms And Ladders, DI-24-001, Civil / Structural – CWP #001 | Diamond Petrochemicals Canada | Powers, Dave | FP | 01 - Industrial | Active
01-26-122 | Enbridge - TBD1 - PO#4950037827 | Enbridge Gas Inc | Powers, Dave | T&M | 01 - Industrial | Active
01-26-123 | Enbridge - TBD2 - PO#4950037207 | Enbridge Gas Inc | Powers, Dave | T&M | 01 - Industrial | Active
01-26-124 | Enbridge - TBD3 - PO#4950037426 | Enbridge Gas Inc | Powers, Dave | T&M | 01 - Industrial | Active
01-25-001 | H. C. Starck - Insulation Services | H.C. Starck Canada Inc. | Powers, Dave | T&M | 01 - Industrial | Active
01-25-234 | H. C. Starck - Insulation Services 2026 | H.C. Starck Canada Inc. | Powers, Dave | T&M | 01 - Industrial | Active
01-26-049 | H. C. Starck Canada - Kiln 1 Drier Upgrade | H.C. Starck Canada Inc. | Powers, Dave | T&M | 01 - Industrial | Active
01-25-002 | H.C.Starck – Pipefitting Services | H.C. Starck Canada Inc. | Powers, Dave | T&M | 01 - Industrial | Active
01-25-235 | H.C.Starck – Pipefitting Services | H.C. Starck Canada Inc. | Powers, Dave | T&M | 01 - Industrial | Active
01-26-017 | Hydrostor - PSV Removal and delivery | Hydrostor | Powers, Dave | T&M | 01 - Industrial | Active
01-26-095 | MN Mechanical - Asbestos on water drains | MN Mechanical | Powers, Dave | T&M | 01 - Industrial | Active
01-26-018 | MN Mechanical - Asbestos remediation in Maintenance garage | MN Mechanical | Powers, Dave | T&M | 01 - Industrial | Active
01-26-046 | Nova Rokeby - ROTA27 Wolverine Management | Nova Chemicals Corporation | Powers, Dave | T&M | 01 - Industrial | Active
01-25-226 | Suncor - 2026 - Kim Daborn - Safety Support | Suncor Energy Inc | Powers, Dave | T&M | 01 - Industrial | Active
01-26-032 | Suncor - 2026 Marc Jolicoeur Planning Support | Suncor Energy Inc | Powers, Dave | T&M | 01 - Industrial | Active
01-25-198 | Suncor - 2027 TA Spring TA Planning Support | Suncor Energy Inc | Powers, Dave | T&M | 01 - Industrial | Active
01-25-200 | Suncor - 2028 TA Planning Support | Suncor Energy Inc | Powers, Dave | T&M | 01 - Industrial | Active
01-26-167 | Suncor - the Cooling Water Line Upgrade Piping | Suncor Energy Inc | Powers, Dave | FP | 01 - Industrial | Active
01-26-093 | Suncor Ethanol - Piping and Insulation Services - Distillation & Dehydration | Suncor Energy Inc | Powers, Dave | T&M | 01 - Industrial | Active
01-26-114 | Suncor Ethanol - Ferm Exchanger piping | Suncor Energy Inc | Powers, Dave | T&M | 01 - Industrial | Active
01-25-228 | Suncor Ethanol - Wolverine 2026 Call in support | Suncor Energy Inc | Powers, Dave | T&M | 01 - Industrial | Active
01-25-205 | University of Guelph - 2025-26 Insulation Improvements (Proj. # 621386) | University of Guelph | Powers, Dave | T&M | 01 - Industrial | Active
01-26-089 | University of Guelph - Insulation on Exposed Ductwork | University of Guelph | Powers, Dave | FP | 01 - Industrial | Active
01-26-195 | Wolverine Eng. - ASME FLANGED AND DISHED 96" OD HEAD - conrex steel | Wolverine Engineering Ltd. | Powers, Dave | FP | 01 - Industrial | Active