| Project No.: | 01-26-020 (26766) | RFI No.: | RFI-126020-004 |
| --- | --- | --- | --- |
| Date: | August 24, 2026 | Discipline: | Mechanical |
| Project Name: | 26766 – BA2107 TLE End-of-Life Replacement |  |  |

| Subject: | TLE Channel Cover Lifting Lugs – Existing Configuration Does Not Match Scope Requirement |
| --- | --- |
| Specifications/Documents/Drawings Referenced or Impacted: |  |
| Scope of Work: 26766 - CWP-G02 Rev 0.1 - 2021489 – IFC, Section 6.1.9 Drawing: EA2102D-049 Rev 0.2, “EA-2102D New Lifting Lug Installation” (Work Package, page 92) Attachment 1: Scope of Work Section 6.1.9 – excerpt Attachment 2: Drawing EA2102D-049 Rev 0.2 (Work Package, page 92) |  |

| Question or Description of Issue: |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Scope of Work document 26766 - CWP-G02 Rev 0.1 - 2021489 – IFC, Section 6.1.9 sets out NOVA’s requirement for lifting lugs on the Transfer Line Exchanger (TLE) channel covers. The clause reads: «INSERT VERBATIM TEXT OF SCOPE SECTION 6.1.9 HERE PRIOR TO ISSUE» Wolverine has completed a field review of the existing TLEs within the scope of this work package. None of the existing TLE channel covers are fitted with lifting lugs in the configuration specified by Section 6.1.9. The only lifting lug arrangement Wolverine has been able to identify on an issued drawing is that shown on Drawing EA2102D-049 Rev 0.2, “EA-2102D New Lifting Lug Installation” (Work Package, page 92, attached). That drawing shows two (2) lugs of SA-387 F5 CL.2 (or SA-387 GR.22 CL.2), 38.1 mm thick, welded at 283.4 mm spacing to a 1210 mm dia. × 180 mm thick SA-336-F5 cover plate. Each lug is rated for a design load of 21,521 lb in-plane only, for use with a Crosby G-2130 13.5 ton shackle. Wolverine draws NOVA’s attention to Note 10 of that drawing, which states: “This change is implemented in April 2022, when EA-2102D channel is installed on EA-2107B TLE tube section. These lifting lugs have been designed for this configuration only. Any future change must be re-evaluated by engineering.” On the basis of Note 10, the existing lug design cannot be replicated on other TLE channel covers without engineering re-evaluation. Wolverine further notes that installation to this detail is not a field-only activity: Notes 4, 5, 8 and 9 of the same drawing require 400°F (204°C) preheat during welding, post weld heat treatment at 1250°F (675°C) for 5 hr 45 min, liquid penetrant examination of the first and final pass of each weld, and a 91 PSIG hydrotest of the channel following completion of welding, all in compliance with TSSA Act O.Reg. 220/01, CSA B51-2019 and ASME BPVC Section VIII Div. 1. Wolverine requests that NOVA review this issue with the Owner’s Engineer and confirm the required path forward. |  |  |  |  |  |  |  |  |
| Originator’s Recommended Solution: |  |  |  |  |  |  |  |  |
| Wolverine requests that NOVA confirm which of the following applies: 1. NOVA holds drawings or records for TLE channel covers fitted with lifting lugs in the configuration described in Section 6.1.9, and will issue them to Wolverine; or 2. Section 6.1.9 requires new lifting lugs to be designed and installed on the in-scope TLE channel covers. If so, Wolverine requests written confirmation that this constitutes a change to the scope as tendered; or 3. The existing EA2102D-049 Rev 0.2 lug configuration is to be adopted as the standard for the in-scope TLE channel covers. If so, engineering re-evaluation is required in accordance with Note 10 of that drawing prior to any fabrication. Wolverine additionally requests confirmation of the specific TLE tag numbers within scope for lifting lug installation. Cost and schedule impact cannot be assessed until the above is confirmed. Should option 2 or option 3 apply, Wolverine will submit a change notice with full cost and schedule impact. |  |  |  |  |  |  |  |  |
| Urgency: | High (3 days) |  |  |  |  |  |  |  |
| Originator: |  |  |  |  |  |  |  |  |
|  | Nitin Joshi |  |  |  | [Title] |  | August 24, 2026 |  |
|  | Name |  | Signature |  | Title |  | Date |  |

| Response: |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Respondent: |  |  |  |  |  |  |  |  |
|  | Name |  | Signature |  | Title |  | Date |  |